## Customer Info
Customer | Project Lead | PM | CEM | Meeting Date | Other Attendees
Meitheal | Jon Astemborski | Jon Ragati | Anna Geeter | 2017-01-13 | Kim, Shannon, Jim

## Requirements
Change Type | Change Description | Platform | QE Process | Additional Notes | JIRA Task | Status | Assignee | Sprint
Add Field | In the product section, have free text options to enter in Product, Lot Number, NDC Number and Facility | Complaints | Inquiry |  | TEST-1185 | In Progress | admin
Remove Field Type | In the complaint determination section, removed manufactured by company | Complaints | Inquiry |  | TEST-1186 | To Do | admin
Modify Field Values | In the compaint details, change the following inputs for the Type category to: Drug Product, Primary Container, Secondary Container, Tertiary Container, Shipping Container, Label, Package Insert | Complaints | Change Control |  | TEST-1187 | In Progress | admin
Modify Field Type | Change Customer to free text | Complaints | Change Control |  | TEST-1188 | To Do | admin
Modify Field Values | Under Location have the following inputs only: None, Laboratory, Manufacturing, Warehouse, Packaging, Formulation, Shipping, Other | EQMS | Quality Event |  | TEST-1189 | Done | admin
Modify Field Type | Change Equipment to free text | EQMS | Quality Event |  | TEST-1190 | To Do | admin
Remove Field Type | Remove Related Supplier Field | EQMS | Quality Event |  | TEST-1191 | Done | admin
Modify Field | Change Supplier Contact Person to just be Contact Person | EQMS | Quality Event |  | TEST-1192 | In Progress | admin
Modify Field Type | Change Product in this spot to just be free text | EQMS | Quality Event |  | TEST-1193 | To Do | admin
Add Field | Add a field Called Facility here as a free text (in the Event Identification section) | EQMS | Quality Event |  | TEST-1194 | To Do | admin
Add Field | Add a Field Called Facility here as a free text (in the Event Identification section) | EQMS | Quality Event | Issue: TEST-1194 already exists. |  | Duplicate

## JIRA Stories
| Complaints | Inquiry | CAPA | Quality Event | Change Control | Assessment | Investigation/Evaluation | Audits | Salesforce Objects | Custom Objects | Global
Key |  | TEST-1182 |  | TEST-1183 | TEST-1184
Title |  | Inquiry |  | Quality Event | Change Control
Description |  | Meitheal |  | Meitheal | Meitheal
Project |  | DELIVERCOM |  | DELIVERCOM | DELIVERCOM
Assignee |  | admin |  | admin | admin
Board |  | TEST Board |  | TEST Board | TEST Board
Sprint |  | TEST Sprint 15 |  | TEST Sprint 15 | TEST Sprint 15