## Customer Info
Customer | Project Lead | PM | CEM | Meeting Date | Other Attendees
Proactiv | Jon Astemborski | Jon Ragati | Adam Helfer | 2017-03-23 | Erle, Silva, Francis, Jim

## Requirements
Change Type | Change Description | Platform | Process | Additional Notes | JIRA Task | Status | Assignee | Sprint
Modify Field Label | Rename Short Description to Title | EQMS | Quality Event |  | DELIVERCOM-354 | Open
Add Picklist Values | Add values to Location Type - will be provided a list by The Proactiv Company | EQMS | Quality Event |  | DELIVERCOM-355 | Open
Hide Field | Hide Equipment from the Event Identification section | EQMS | Quality Event |  | DELIVERCOM-356 | Open
Hide Field | Hide Related Supplier from the Event Identification section | EQMS | Quality Event |  | DELIVERCOM-357 | Open
Modify Field | Modify Description so that it spans two columns | EQMS | Quality Event |  | DELIVERCOM-358 | Open
Modify Field | Move Immediate Action beneath Description and have it span two columns | EQMS | Quality Event |  | DELIVERCOM-359 | Open
Hide Field | Hide Supplier Contract Person from the Event Identification Section | EQMS | Quality Event |  | DELIVERCOM-360 | Open
Hide Field | Hide Probability Measure from the Risk Analysis section | EQMS | Quality Event |  | DELIVERCOM-361 | Open
Hide Field | Hide Severity Measure from the Risk Analysis section | EQMS | Quality Event |  | DELIVERCOM-362 | Open
Hide Field | Hide Occurance Measure from the Risk Analysis section | EQMS | Quality Event |  | DELIVERCOM-363 | Open
Remove Process Builder Automation | Remove Process Builder Automation automically creating a Quality Event Investigation when Investigation Required? is set to yes | EQMS | Quality Event |  | DELIVERCOM-364 | Open
Remove Field Dependency | Remove dependency for Investigation Required?, Root Cause, Investigation Completed? | EQMS | Quality Event |  | DELIVERCOM-365 | Open
Investigate Removal of Field | Remove both Investigation Completed? and Investigation Required? from the Investigation section. | EQMS | Quality Event | The Proactiv Company wants to capture QEI within the QE record itself. Thereby eliminating the need for automating QEI record creation. Since Investigation information will be captured within the Investigation section - they find it superfluous to provide information for Investigation Required? and Investigation Completed. Investigation will be needed to see how to navigate the workflow validation rules assuming these fields will not be used. | DELIVERCOM-366 | Open
Hide Field | Hide Document Update? | EQMS | Quality Event |  | DELIVERCOM-367 | Open
Hide Field | Hide Prority within Investigation Detail | EQMS | Quality Event Investigation | May not be needed as they will be capturing all information within QE. | DELIVERCOM-368 | Open
Hide Field | Hide Impact Analysis from CAPA Risk Analysis | EQMS | CAPA |  | DELIVERCOM-369 | Open
Hide Field | Hide Likelihood of detection from CAPA Risk Analysis | EQMS | CAPA |  | DELIVERCOM-370 | Open
Hide Field | Hide Likelihood of occurrence from CAPA Risk Analysis | EQMS | CAPA |  | DELIVERCOM-371 | Open
Hide Field | Hide Severity of impact from CAPA Risk Analysis | EQMS | CAPA |  | DELIVERCOM-372 | Open
Modify Field | Move Investigation Required? to the bottom of CAPA Identification | EQMS | CAPA |  | DELIVERCOM-373 | Open
Hide Section | Hide the Section banner CAPA Risk Analysis | EQMS | CAPA |  | DELIVERCOM-374 | Open
Investigate Workflow and Automation Changes | Eliminate the automation of CAPA Investigation and CAPA Plan record creation, as well as any validation requiring information regrarding CAPA Investigation/Plan to advance the records workflow. | EQMS | CAPA | The Proactiv Company wants to capture CAPA Investigations and CAPA Plans within the CAPA record itself. Thereby eliminating the need for automating CAPA Investigation/Plan record creation. Since this information will be captured within the CAPA record - they find it superfluous to provide information for Investigation Required? and Effectiveness Check Required? as well as close out any CAPA Investigations or CAPA Plans prior to advancing the parent CAPA. Investigation will be needed to see how to navigate the workflow validation rules assuming these fields will not be used. | DELIVERCOM-375 | Open
Modify Field Label | Rename Short Description to Title | EQMS | Change Control |  | DELIVERCOM-376 | Open
Hide Field | Hide Site from Change Control Detail | EQMS | Change Control |  | DELIVERCOM-377 | Open
Hide Field | Hide Supervisor/Manager from Change Control Detail supervisor/manager quality contact | EQMS | Change Control |  | DELIVERCOM-378 | Open
Hide Field | Hide Quality Contact from Change Control Detail | EQMS | Change Control |  | DELIVERCOM-379 | Open
Add Picklist Values | Add picklist values to Type - will be provided list | EQMS | Change Control | The Proactiv Company will provide a list of values | DELIVERCOM-380 | Open
Hide Field | Hide Emergency Change? From Change Control Information | EQMS | Change Control |  | DELIVERCOM-381 | Open
Hide Field | Hide GxP Change? From Change Control Information | EQMS | Change Control |  | DELIVERCOM-382 | Open
Modify Field | Modify Change Description to span two columns | EQMS | Change Control |  | DELIVERCOM-383 | Open
Modify Field | Modify Justification to span two columns | EQMS | Change Control |  | DELIVERCOM-384 | Open
Add Section | Add section title Impact underneath Change Control Information | EQMS | Change Control |  | DELIVERCOM-385 | Open
Add Field | Add free-text field Impact Assessment under Impact section | EQMS | Change Control |  | DELIVERCOM-386 | Open
Add Field | Add Change Plan as free-text field to Change Control Information | EQMS | Change Control |  | DELIVERCOM-387 | Open
Add Field | Add Implementation Plan as free-text field to Change Control Information | EQMS | Change Control |  | DELIVERCOM-388 | Open
Hide Field | Hide Product Lot Number(s) from Change Details | EQMS | Change Control |  | DELIVERCOM-389 | Open
Hide Field | Hide Dosage from Change Details | EQMS | Change Control |  | DELIVERCOM-390 | Open
Hide Field | Hide Form from Change Details | EQMS | Change Control |  | DELIVERCOM-391 | Open
Hide Field | Hide Product Comment from Change Details | EQMS | Change Control |  | DELIVERCOM-392 | Open
Hide Field | Hide Documents Affected? from Change Details | EQMS | Change Control |  | DELIVERCOM-393 | Open
Hide Field | Hide Document Type from Change Details | EQMS | Change Control |  | DELIVERCOM-394 | Open
Hide Field | Hide Document Reference? from Change Details | EQMS | Change Control |  | DELIVERCOM-395 | Open
Hide Field | Hide Document Name from Change Details | EQMS | Change Control |  | DELIVERCOM-396 | Open
Hide Field | Hide Document Comment from Change Details | EQMS | Change Control |  | DELIVERCOM-397 | Open
Hide Field | Hide Material(s) Affected? from Change Details | EQMS | Change Control |  | DELIVERCOM-398 | Open
Hide Field | Hide Material Number from Change Details | EQMS | Change Control |  | DELIVERCOM-399 | Open
Hide Field | Hide Material Lot Number(s) from Change Details | EQMS | Change Control |  | DELIVERCOM-400 | Open
Hide Field | Hide Material Name from Change Details | EQMS | Change Control |  | DELIVERCOM-401 | Open
Hide Field | Hide Equipment Affected? from Change Details | EQMS | Change Control |  | DELIVERCOM-402 | Open
Hide Field | Hide Equipment Description from Change Details | EQMS | Change Control |  | DELIVERCOM-403 | Open
Hide Field | Hide Equipment ID from Change Details | EQMS | Change Control |  | DELIVERCOM-404 | Open
Hide Field | Hide Material/Equipment Comment from Change Details | EQMS | Change Control |  | DELIVERCOM-405 | Open
Modify Field Label | Rename Product Number to Item Code | EQMS | Change Control |  | DELIVERCOM-406 | Open
Modify Field | Move Product Number ( Item Code ) to the right of Product | EQMS | Change Control |  | DELIVERCOM-407 | Open
Add Field | Add free-text field Action Plan Summary in Change Details and have it span 2 columns | EQMS | Change Control |  | DELIVERCOM-408 | Open
Investigate Workflow and Automation Changes | Eliminate the need for Change Control Effectiveness Check and Change Control Plan record creation, as well as any validation requiring information regrarding Change Control Effectiveness Check and Change Control Plan to advance the records workflow. ( All information should be captured in Change Control ) | EQMS | Change Control | The Proactiv Company wants to capture Change Control Effectiveness Check and Change Control Plan within the Change Control record itself. Thereby eliminating the need for Change Control Effectiveness Check and Change Control Plan record creation. Investigation will be needed to see how to navigate the workflow validation rules assuming these fields will not be used. | DELIVERCOM-409 | Open
Add Section | Add section titled Implementation Verification |  | Change Control |  | DELIVERCOM-410 | Open
Add Field | Add Implementation Verification as a free-text field in the Implementation Verification section |  | Change Control |  | DELIVERCOM-411 | Open
Add Field | Create field Severity as a picklist with values: level 1, level 2, level 3. However, do not add to layout | EQMS | Change Control |  | DELIVERCOM-412 | Open
Modify Public Groups | The Change Control workflow should be modified so that everything from Change Control in Planning downward should be handled by the public group QE. The Owner should still be the initiator. | EQMS | Change Control |  | DELIVERCOM-413 | Open
Modify Workflow | Modify workflow to remove the steps under the original SME public group. At the state Implementation Complete the record should route directly to route to Pending QA Approval Implementation Complete or Pending QA Approval EC Not Required depending on the branch taken. | EQMS | Change Control |  | DELIVERCOM-414 | Open

## JIRA Stories
| Complaints | Inquiry | CAPA | Quality Event | Change Control | Assessment | Investigation/Evaluation | Audits | Salesforce Objects | Custom Objects | Global
Key |  |  | DELIVERCOM-351 | DELIVERCOM-352 | DELIVERCOM-353
Title |  |  | CAPA | Quality Event | Change Control
Description |  |  | Proactiv | Proactiv | Proactiv
Project |  |  | DELIVERCOM | DELIVERCOM | DELIVERCOM
Assignee
Board
Sprint